## ADMINISTRATION WORKPLAN
Powers & Sullivan, LLC |  | * All items include Charlie Sumner,
2020 Management Letter | "Town-Wide" - Findings & Recommendations | Lisa Souve and Mary McIsaac as
stakeholders.
MATERIAL WEAKNESS | Auditor's Recommendations | Stakeholders* | Internal Action Plan Status | Target Date for Completion
CASH RECONCILIATIONS | Complete a comprehensive evaluation of the cash management process with | Town Treasurer
| the goal of completing full reconciliations of cash on a monthly basis. | Town Departments, as needed | Phase I- Gathering of Documents; Interview stakeholders | To Be Determined
| Enhance and update the cash reconciliation policy and formally document |  | Phase II- Examine data and identify errors and omissions
| any cash reconciliation procedures as well as ensure compliance with any |  | Phase III- Document Corrective Action(s)
| such policy or procedures. |  | Phase IV-Complete all policy/procedure drafts; Review with mgmt.
OTHER COMMENTS | Auditor's Recommendations | Stakeholders* | Internal Action Plan Status | Target Date for Completion
MAINTAINING PROPER VENDOR | Perform a review of the vendor listing. | Assistant Town Accountant
RECORDS AND DATABASE |  |  | Phase I- Gathering of Documents; Interview stakeholders | To Be Determined
| Ensure that a vendor database is accurate and complete. |  | Phase II- Examine data and identify errors and omissions
Phase III- Document Corrective Action(s)
| Obtain current W-9 forms for each vendor on file. |  | Phase IV-Complete all policy/procedure drafts; Review with mgmt.
SUPPORTING DOCUMENTATION FOR | Establish and document formal internal control policies over the Town's | Payroll Coordinator (Asst. T/Acct)
THE TOWN'S PAYROLL PROCESS | payroll function. | Town Treasurer | Phase I- Gathering of Documents; Interview stakeholders | To Be Determined
| Establish the use of standardized forms to track payrates earned, hours | Town Departments, as needed | Phase II- Examine data and identify errors and omissions
| worked, paid time-off and accrual balances. |  | Phase III- Document Corrective Action(s)
| Adopt a standard payroll period. |  | Phase IV-Complete all policy/procedure drafts; Review with mgmt.
Conduct a full review of current bargaining unit contracts.
Implement procedures to ensure compliance with such policies.
AUTOMATION OF COMPENSATED | Record and monitor compensated absences liability through the payroll | Payroll Coordinator (Asst. T/Acct) | Phase I- Gathering of Documents; Interview stakeholders
ABSENCES. | system. | Town Departments, as needed | Phase II- Examine data and identify errors and omissions | To Be Determined
| Implement an automated system to monitor compensated absences. |  | Phase III- Document Corrective Action(s)
Phase IV-Complete all policy/procedure drafts; Review with mgmt.
RECORDING INTERFUND TRANSFERS | Implement procedures to reconcile any transfers as budgeted at Town | Town Treasurer | Phase I- Gathering of Documents; Interview stakeholders
AND THE CONTRIBUTION TO THE | Meeting to transfers recorded to the general ledger. |  | Phase II- Examine data and identify errors and omissions | To Be Determined
OPEB TRUST FUND |  |  | Phase III- Document Corrective Action(s)
Phase IV-Complete all policy/procedure drafts; Review with mgmt.
COMINGLING THE STABLIZATION | Utilize funds in the general ledger to appropriately track and record the | Town Treasurer | Phase I- Gathering of Documents; Interview stakeholders
FUNDS AND OPEB TRUST FUND WITH | balances and activity in these funds separately from other expendable |  | Phase II- Examine data and identify errors and omissions | To Be Determined
OTHER FUNDS | trust funds….. |  | Phase III- Document Corrective Action(s)
Phase IV-Complete all policy/procedure drafts; Review with mgmt.
ACCOUNTING FOR THE PEG CABLE | Record PEG cable access operations in compliance with DOR | Fund Management personnel | Phase I- Gathering of Documents; Interview stakeholders
ACCESS FUND | guidelines. |  | Phase II- Examine data and identify errors and omissions | To Be Determined
Phase III- Document Corrective Action(s)
Phase IV-Complete all policy/procedure drafts; Review with mgmt.
MAINTAINING A BUDGET RECONCILIATION | Implement a process to verify budgetary compliance. | Assistant Town Accountant, as needed | Phase I- Gathering of Documents; Interview stakeholders
AND ACCOUNTING FOR THE GENERAL FUND | Reconcile Town meeting votes to the amounts on the ReCap to the amounts |  | Phase II- Examine data and identify errors and omissions | To Be Determined
BUDGET | in the General Ledger (VADAR). |  | Phase III- Document Corrective Action(s)
Phase IV-Complete all policy/procedure drafts; Review with mgmt.
SUPPORT FOR RECEIVABLES | Establish a policy to reconcile all receivables monthly with supporting | Tax Collector | Phase I- Gathering of Documents; Interview stakeholders
| documentation and ensure that all variances are resolved timely. | Town Departments, as Needed | Phase II- Examine data and identify errors and omissions | To Be Determined
| BETTERMENTS- Establish an internal control policy and procedures for the |  | Phase III- Document Corrective Action(s)
| recording and reconciliation of betterments monthly. |  | Phase IV-Complete all policy/procedure drafts; Review with mgmt.
RESERVE FOR ABATEMENTS/OVERLAY | The Town Accountant and the Town Assessor reconcile abatement activity | Town Assessor | Phase I- Gathering of Documents; Interview stakeholders
| and balances on a monthly basis. |  | Phase II- Examine data and identify errors and omissions | To Be Determined
Phase III- Document Corrective Action(s)
Phase IV-Complete all policy/procedure drafts; Review with mgmt.
GENERAL LEDGER REPORTING AND | Review each project within the accounting structure across each of the | Assistant Town Accountant, as needed | Phase I- Gathering of Documents; Interview stakeholders
MAINTENANCE | Town's funds. |  | Phase II- Examine data and identify errors and omissions | To Be Determined
| Verify each project's current balance. |  | Phase III- Document Corrective Action(s)
| Establish policies and procedures for all project activity. |  | Phase IV-Complete all policy/procedure drafts; Review with mgmt.
ENCUMBRANCES AND THE USE OF | Implement a process to utilize purchase orders to strengthen controls over | Assistant Town Accountant, as needed | Phase I- Gathering of Documents; Interview stakeholders
PURCHASE ORDERS | the expenditure and year-end encumbrance processes. | Town Departments | Phase II- Examine data and identify errors and omissions | To Be Determined
Phase III- Document Corrective Action(s)
Phase IV-Complete all policy/procedure drafts; Review with mgmt.
CAPITAL ASSET ACCOUNT MAINTENANCE | Perform a full review of the capital asset inventory. | Identify the Custodian/Recordkeeper of | Phase I- Gathering of Documents; Interview stakeholders
| Implement procedures to ensure proper management of the software | Fixed Asset Inventory | Phase II- Examine data and identify errors and omissions | To Be Determined
| system to verify that capital asset additions, disposals, and depreciation |  | Phase III- Document Corrective Action(s)
| are properly tracked and recorded in the Town's financial statements. |  | Phase IV-Complete all policy/procedure drafts; Review with mgmt.
INADEQUATE CONTROLS OVER THE GENERAL | Management review of individuals, and the roles and responsibilities of | All Finance Officials and their staff | Phase I- Gathering of Documents; Interview stakeholders
LEDGER AND FINANCIAL STATEMENTS | the accounting and finance departments. |  | Phase II- Examine data and identify errors and omissions | To Be Determined
Phase III- Document Corrective Action(s)
Phase IV-Complete all policy/procedure drafts; Review with mgmt.